## 00_Dashboard
MINGO — PHASE 2 UX/UI QA CONTROL
Codex execution: 94/94 PASS (44/44 P0). Screen-reader session BLOCKED. Independent QC/QA and signoffs pending.
Candidate KPI | ACTIVE — TECHNICAL RETEST PASS / GATE HOLD | Live test metric | 94 | Exit criterion | Required | 44/44 Independent PASS | Owner
Phase status | NOT PASSED | Total cases | 0 | All P0 test cases pass | 100% | 0 open P0/P1 | QA
Gate | NOT PASSED | P0 cases | 0 | All P0/P1 defects closed | 0 open | 94/94 Independent PASS | QA/Tech
Screens | 57 | PASS | 0 | Overall executed pass rate | ≥95% | 100% Codex | QA
Shared components | 18 | FAIL | 0 | PRD traceability | 16/16 | Interactive SR/TalkBack BLOCKED | QC
PRD traceability | 16 | BLOCKED | 0 | Accessibility mandatory checks | PASS | Tech Lead PENDING | QA
Prepared QC/QA cases | V3.2.0 — unchanged | NOT RUN | 0 | Developer handoff | ACCEPTED | Product/Owner PENDING | Tech Lead
Architecture baseline | V3.2.0 — unchanged | Open P0/P1 defects | 0 | Product/Owner signoff | SIGNED | PENDING | Owner/Product
Phase 3 | DEFERRED
Independent R1 retest | 94/94 canonical PASS independently; P2-D001..D020 CLOSED. New P2-D021 is non-production toolbar portability and is a defer candidate.
Gate decision | NOT PASSED — blocked by interactive screen-reader/TalkBack + Tech Lead + Product/Owner signoff.

## 01_Screen_Inventory
PHASE 2 SCREEN INVENTORY
Canonical screen IDs/routes for learner and staff.
Screen ID | Surface | Area | Name | Route | Purpose | Entry | Actions | Required states | Critical rules
L-001 | Learner | Entry | Launch | /launch | App launch and bootstrap handoff | App start | Continue automatically | Loading, error, offline bootstrap | No business decision performed here
L-002 | Learner | Onboarding | Welcome | /welcome | Explain Mingo promise and let learner start | First use | Start learning | Default, loading | No efficacy/mastery claim
L-003 | Learner | Onboarding | Goal | /onboarding/goal | Optional learner goal selection | Welcome | Continue / Skip for now | Default, selected, error | Goal cannot rewrite measured skill
L-004 | Learner | Onboarding | Placement Offer | /onboarding/placement | Offer short optional placement | Goal | Take placement / Start without it | Default, unavailable | Placement optional; missing evidence allowed
L-005 | Learner | Onboarding | Placement Question | /placement/:step | Run provisional Vocabulary/Grammar/Listening item | Placement offer | Submit / Skip domain where allowed | Ready, selected, submitting, feedback, audio unavailable | No certified CEFR claim; server authoritative later
L-006 | Learner | Onboarding | Placement Result | /placement/result | Show provisional starting state and uncertainty | Placement finish | Go to Home | Complete, insufficient-evidence | Qualitative/provisional language only
L-010 | Learner | Main | Home | /home | Answer what to do next and why | Main shell | Start/resume cycle | Online, offline, syncing, nothing-due, recommendation-unavailable | Reason copy must match logged reason; no risk/mastery percentage
L-011 | Learner | System | Home Offline | /home?offline=1 | Home with offline status and device-saved distinction | Connectivity loss | Continue available offline work | Offline, queued | Queued is not server-confirmed
L-012 | Learner | System | Home Syncing | /home?syncing=1 | Show background synchronization without blocking navigation | Connectivity restore | View sync status | Syncing, partial | No duplicate progress/reward from retries
L-020 | Learner | Main | Learn Hub | /learn | Start or resume finite learning cycle | Learn tab | Start / Resume | Ready, resume, content-gap | No infinite feed
L-021 | Learner | Learning | Cycle Intro | /learn/cycle/intro | Show objective, reason and approximate duration | Cycle selected | Begin cycle | Ready, offline-capable, content-unavailable | ~5 min is configurable hypothesis; objective/reason explicit
L-022 | Learner | Learning | Review Item | /learn/cycle/review | Due/prerequisite review within bounded cycle | Cycle start | Answer / Skip | Ready, selected, submitting, feedback, skipped | At most one justified due/prerequisite insertion in default policy hypothesis
L-023 | Learner | Learning | Learn Content | /learn/cycle/learn | Short explanation/example/audio/context | Review or cycle start | Continue | Ready, audio-loading, audio-unavailable | Reading explanation alone is not mastery
L-024 | Learner | Learning | Retrieve Item | /learn/cycle/retrieve | Unaided retrieval attempt | Learn | Submit / Hint / Skip | Ready, hinted, selected, submitting, correct, incorrect, retry | First response preserved; assisted != unaided
L-025 | Learner | Learning | Transfer Item | /learn/cycle/transfer | Change cue/context/modality within objective | Retrieve | Submit / Skip | Ready, selected, feedback | Transfer != challenge; no automatic level change
L-026 | Learner | Learning | Check Intro | /learn/cycle/check-intro | Explain independent Check context | Transfer | Start Check | Ready | No pre-submit hint in Check
L-027 | Learner | Learning | Check Item | /learn/cycle/check | Independent assessment item | Check intro | Submit | Ready, selected, submitting, result, audio-policy | No hint before submit; listening condition recorded; client replay telemetry not score authority
L-028 | Learner | Learning | Correct Feedback | /learn/feedback/correct | Give concise explanatory positive feedback | Correct response | Continue | Default | Reward/copy cannot imply validated mastery from one answer
L-029 | Learner | Learning | Incorrect / Retry Feedback | /learn/feedback/retry | Explain error and offer practice retry where policy allows | Wrong practice response | Try again / Continue | Retry available, retry used, retry exhausted | Retry correct never overwrites first wrong
L-030 | Learner | Overlay | Hint Panel | /learn/hint | Provide typed assistance in practice | Hint request | Use hint / Close | Default, unavailable | Hint use marks evidence assisted
L-031 | Learner | Overlay | Skip Confirmation | /learn/skip | Confirm skip without shame or false completion | Skip request | Skip for now / Keep trying | Default | Skip != completion/mastery/streak
L-032 | Learner | Learning | Cycle Summary | /learn/cycle/summary | Explicit closure, practiced evidence and next step | Cycle complete | Done for now / Continue learning | Complete, partial, sync-queued | No fake mastery %; user explicitly starts another cycle
L-033 | Learner | Learning | Resume Cycle | /learn/resume | Resume preserved finite cycle | Interrupted cycle | Resume / Leave for now | Resume, stale-content refresh | No duplicate submit on resume
L-040 | Learner | Main | Course Map | /course | Browse objectives and broader path | Course tab | Open objective / Preview locked | Open, due-review, locked, empty | Preview does not unlock/progress
L-041 | Learner | Course | Objective Detail | /course/objective/:id | Explain objective, evidence and eligibility | Course map | Start eligible practice / Review | Eligible, due, locked, insufficient-evidence | Prerequisite guardrail remains authoritative
L-042 | Learner | Course | Locked Preview | /course/objective/:id/preview | Safe preview of locked objective | Locked objective | Back / Work on prerequisite | Preview | No score/progress/unlock from preview
L-050 | Learner | Main | Profile | /profile | Goal, qualitative learning evidence and settings entry | Profile tab | Open evidence/settings | Default, insufficient-evidence | Engagement/streak not presented as mastery
L-051 | Learner | Profile | Evidence Detail | /profile/evidence/:domain | Show observations, uncertainty and missing evidence | Profile | Review related objective | Building, more-evidence-needed | No diagnosis or precise mastery percentage without validated model
L-052 | Learner | Profile | Goal Settings | /profile/goal | Edit learner intent | Profile | Save / Clear | Default, saved, error | Goal change does not rewrite competence
L-053 | Learner | Profile | Learning Preferences | /profile/preferences | Accessibility and learning preferences | Profile | Save | Default, saved | Preference cannot bypass required eligibility rules
L-054 | Learner | Profile | Offline Downloads | /profile/offline | Manage available offline content packages | Profile | Download / Remove / Refresh | Available, downloading, downloaded, expired, failed | Access grant/package rules remain server-authoritative
L-060 | Learner | System | Sync Queue | /sync | Explain queued/synced items without technical jargon | Sync status tap | Retry / Close | Queued, syncing, synced, partial | Queued != accepted; canonical progress waits server result
L-061 | Learner | System | Sync Error | /sync/error | Recover retryable sync failure | Sync fail | Retry now / Later | Retryable, re-auth-required, canonical-refresh | Never encourage duplicate manual resubmission
L-062 | Learner | System | Generic Error | /error | Recover from unexpected non-destructive error | Runtime error | Retry / Go home | Recoverable, fatal | No false success state
L-063 | Learner | System | Nothing Due / Content Gap | /learn/empty | Honest empty/content unavailable state | No eligible cycle | Explore course / Sync content | Nothing-due, no-valid-cycle, media-unavailable | Do not fabricate cycle/recommendation
L-064 | Learner | System | Re-auth Required | /reauth | Explain account/session action required | Auth/session invalid later | Sign in again | Default | Phase 3 implements auth; no local permission bypass
S-001 | Staff | Entry | Staff Entry | /staff | Role-aware staff shell entry placeholder | Staff app launch | Enter authorized workspace | Loading, access-required | Actual authentication/authorization belongs Phase 3
S-010 | Staff | Main | Dashboard | /staff/dashboard | Operational overview and pending work | Staff shell | Open work queue | Default, empty, partial | Metrics must identify time range/source
S-020 | Staff | Learners | Learner List | /staff/learners | Search/filter assigned learners | Learners nav | Open learner | Loading, empty, filtered, error | Role visibility is not authorization
S-021 | Staff | Learners | Learner Overview | /staff/learners/:id | Evidence-based learner overview | Learner list | Open evidence/activity/intervention | Default, insufficient-evidence, access-denied | No mental-state diagnosis; raw risk not default to content admin
S-022 | Staff | Learners | Learner Evidence | /staff/learners/:id/evidence | Review learning/engagement evidence separately | Learner overview | Inspect evidence | Loading, no-evidence | Mastery != risk; uncertainty visible
S-023 | Staff | Learners | Learner Activity | /staff/learners/:id/activity | Auditable recent learning/exposure/activity history | Learner overview | Inspect record | Default, empty | Historical revision pinning preserved
S-030 | Staff | Content | Content Library | /staff/content | Browse/search drafts/published revisions | Content nav | Create draft / Open item | Default, empty, filtered | Published revision immutable
S-031 | Staff | Content | Content Draft Editor | /staff/content/drafts/:id | Author draft content and learning metadata | Library/new draft | Save draft / Preview / Submit review | Dirty, saving, saved, validation-error | Draft may change; published content cannot
S-032 | Staff | Content | Content Preview | /staff/content/drafts/:id/preview | Preview learner rendering before review | Editor | Back to edit / Submit review | Mobile preview, audio unavailable | Preview is not publication
S-033 | Staff | Content | Source & License | /staff/content/drafts/:id/source | Capture provenance, license and attribution | Editor | Save provenance | Complete, incomplete, blocked | Public access alone != reuse permission
S-034 | Staff | Content | Review Queue | /staff/content/review | List items awaiting editorial/license review | Content nav | Open review | Empty, filtered | Reviewer actions require later server permission
S-035 | Staff | Content | Review Detail | /staff/content/review/:id | Review content, answers, media, provenance | Review queue | Approve / Request changes | Reviewing, blocked-license, validation-error | Cannot approve missing license/provenance gate
S-036 | Staff | Overlay | Publish Confirmation | /staff/content/publish/:id | Confirm creation of immutable published revision | Approved review | Publish revision / Cancel | Ready, publishing, failed | Publish creates new immutable revision; no edit-in-place
S-037 | Staff | Content | Published Revision | /staff/content/published/:id | Inspect immutable revision/history | Library/publish | Create new draft from revision | Published, retired, revoked | Historical attempt remains pinned
S-040 | Staff | Interventions | Interventions | /staff/interventions | Future queue of support actions | Sidebar | Open intervention | Placeholder, empty | Phase 11/12 domain behavior not implemented in Phase 2
S-041 | Staff | Interventions | Intervention Detail | /staff/interventions/:id | Show reason/evidence/decision/exposure/execution/outcome structure | Interventions | Record later action | Placeholder, unavailable | Recommendation lifecycle layers remain distinct
S-050 | Staff | Analytics | Analytics Overview | /staff/analytics | Future operational/learning analytics shell | Sidebar | Open metric view | Placeholder, no-data | Event time/known time/source context required
S-051 | Staff | Analytics | Metric Detail | /staff/analytics/:metric | Inspect metric definition, cohort and time window | Analytics overview | Change filters | Placeholder, insufficient-data | No hidden denominator or future-data leakage
S-060 | Staff | Admin | Administration | /staff/admin | Entry to role/config/audit operations | Sidebar | Open admin area | Placeholder, access-denied | Phase 3/13 define authorization/security
S-061 | Staff | Admin | Roles & Permissions | /staff/admin/roles | Future role management shell | Administration | Inspect role | Placeholder | UI visibility never substitutes backend authz
S-062 | Staff | Admin | Audit Log | /staff/admin/audit | Future privileged audit view | Administration | Inspect event | Placeholder, filtered | Privileged actions audited

## 02_State_Catalog
SHARED COMPONENT / STATE CATALOG
Mandatory non-happy-path states.
Component ID | Component | Required states | Invariant / UX rule
C-001 | AppShell | loading, ready, offline, sync-warning, access-required | Navigation shell never performs business authorization.
C-002 | PrimaryButton | default, pressed, focus, disabled, loading | One dominant action per view where possible; disabled reason exposed when important.
C-003 | AnswerOption | idle, selected, focus, disabled, correct, incorrect | Color is never the only correctness signal; selection is not submission.
C-004 | QuestionCard | ready, submitting, locked, audio-unavailable | Check mode can remove hint action without changing visual identity beyond clear context label.
C-005 | FeedbackPanel | correct, incorrect, retry-available, assisted, final | Retry result never rewrites first-response language/history.
C-006 | HintPanel | available, open, used, unavailable | Only in practice contexts; using it marks assisted evidence.
C-007 | CycleProgress | role-steps, item-progress, complete | Show finite scope; never mimic infinite feed.
C-008 | RecommendationCard | due-review, current-objective, prerequisite-gap, recent-error, transfer, challenge, unavailable | Reason must match auditable reason code; no inferred mental-state copy.
C-009 | SyncBanner | offline, queued, syncing, synced, partial, failed, reauth | Distinguish device-saved from server-synced.
C-010 | EvidenceCard | observed, building, needs-more-evidence, unavailable | No fake mastery percentage or diagnosis.
C-011 | ObjectiveCard | current, open, due, locked, preview | Preview cannot produce completion/unlock.
C-012 | AudioControl | ready, playing, paused, loading, unavailable, play-limit-reached | Client playback count is telemetry, never canonical score authority.
C-013 | EmptyState | nothing-due, no-content, no-search-results, no-data | Never fabricate recommendation/completion.
C-014 | ErrorState | retryable, non-retryable, reauth, canonical-refresh | Recovery action must not create duplicate business command.
C-015 | ContentStatusBadge | draft, in-review, approved, published, retired, revoked | Published is immutable; edit action creates new draft/revision.
C-016 | ContentEditor | clean, dirty, saving, saved, validation-error, conflict | Source/license completeness shown before publish.
C-017 | DataTable | loading, populated, empty, filtered, error | Keyboard accessible; row action permission checked server-side later.
C-018 | ModalOrSheet | open, processing, error | Destructive/irreversible actions have explicit confirmation and result.

## 03_PRD_Traceability
PRD → UX → QA TRACEABILITY
PRD-01..16 mapped to UX surfaces and named QA cases.
PRD | Requirement | Screens | Components | QA cases
PRD-01 | Finite objective-based cycle with clear closure | L-020,L-021,L-022,L-023,L-024,L-025,L-026,L-027,L-032 | C-007 | QA-LRN-001,QA-LRN-002,QA-LRN-012
PRD-02 | First response preserved; guided retry in practice | L-024,L-029 | C-003,C-005 | QA-LRN-006,QA-LRN-007
PRD-03 | Typed hints; assisted != unaided; no pre-submit hint in Check | L-024,L-027,L-030 | C-006 | QA-LRN-008,QA-LRN-013
PRD-04 | Skip logged; not completion/mastery | L-022,L-024,L-031 | C-005 | QA-LRN-009,QA-BIZ-003
PRD-05 | Listening replay support and assessment context | L-005,L-023,L-027 | C-012 | QA-LRN-014,QA-BIZ-005
PRD-06 | Vocabulary/grammar learning sequence | L-023,L-024,L-025,L-027 | C-004 | QA-LRN-004,QA-LRN-005
PRD-07 | Bounded step-up challenge | L-010,L-041 | C-008,C-011 | QA-BIZ-006
PRD-08 | Learner focus with bounded due/prerequisite insertion | L-010,L-021,L-022,L-041 | C-008 | QA-BIZ-007
PRD-09 | Optional short placement; provisional result | L-004,L-005,L-006 | C-007 | QA-LRN-015,QA-LRN-016
PRD-10 | Optional goal; qualitative profile/evidence | L-003,L-050,L-051,L-052 | C-010 | QA-LRN-017,QA-BIZ-008
PRD-11 | Daily target/streak distinct from mastery | L-010,L-050 | C-010 | QA-BIZ-009
PRD-12 | Meaningful rewards only | L-032,L-050 | C-010 | QA-BIZ-010
PRD-13 | Course map, locked preview, evidence-backed reason | L-010,L-040,L-041,L-042 | C-008,C-011 | QA-LRN-018,QA-BIZ-011
PRD-14 | Licensed immutable content and revision pinning | S-030,S-033,S-035,S-036,S-037,L-041 | C-015,C-016 | QA-STF-006,QA-STF-007,QA-BIZ-012
PRD-15 | Command/telemetry/lifecycle separation; offline idempotent/time semantics | L-011,L-012,L-060,L-061,S-050 | C-009,C-014 | QA-OFF-001,QA-OFF-002,QA-OFF-004,QA-BIZ-013
PRD-16 | Usable deterministic fallback with ML/recommendation disabled | L-010,L-020,L-063 | C-008,C-013 | QA-LRN-019,QA-BIZ-014

## 04_QA_Test_Cases
PHASE 2 QA TEST CASES
QA updates Status/Owner/Evidence/Defect; never rewrite Expected just to pass.
Test ID | Type | Area | Priority | Requirement | Title | Precondition | Steps | Expected | Owner | Status | Evidence | Defect | Retest note
QC-001 | QC | Artifact QC | P0 |  | Required Phase 2 artifacts exist | Phase 2 package extracted | Inspect relevant artifacts. | Every file in handoff index exists and opens. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QC-002 | QC | Artifact QC | P0 |  | V3.2 remains untouched | Phase 2 package extracted | Inspect relevant artifacts. | No Phase 2 artifact silently modifies original V3.2 source. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QC-003 | QC | Artifact QC | P0 |  | Phase boundary is explicit | Phase 2 package extracted | Inspect relevant artifacts. | Docs identify Phase 3+ behavior as future/deferred, not implemented. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QC-004 | QC | Artifact QC | P0 |  | Screen IDs unique | Phase 2 package extracted | Inspect relevant artifacts. | All learner/staff screen IDs are unique and traceable. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QC-005 | QC | Artifact QC | P0 |  | Routes documented | Phase 2 package extracted | Inspect relevant artifacts. | Every inventory screen has a route or overlay identity. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QC-006 | QC | Artifact QC | P0 |  | PRD traceability complete | Phase 2 package extracted | Inspect relevant artifacts. | PRD-01..PRD-16 all map to UX surfaces and QA cases. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QC-007 | QC | Artifact QC | P0 |  | Locked vs hypothesis language | Phase 2 package extracted | Inspect relevant artifacts. | 5m/retry/replay/placement thresholds are labelled hypotheses where applicable. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QC-008 | QC | Artifact QC | P0 |  | No false learning claims | Phase 2 package extracted | Inspect relevant artifacts. | No precise mastery/diagnosis/efficacy claim appears in learner copy. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QC-009 | QC | Artifact QC | P0 |  | No credential material | Phase 2 package extracted | Inspect relevant artifacts. | No password/token/secret URL in Phase 2 package. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QC-010 | QC | Artifact QC | P0 |  | Prototype is self-contained | Phase 2 package extracted | Inspect relevant artifacts. | No external CDN/network dependency is required to render prototype. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-NAV-001 | QA | Navigation/IA | P1 |  | Learner top-level IA | Prototype available | Open prototype learner shell. | Bottom navigation exposes only Home, Learn, Course, Profile. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-NAV-002 | QA | Navigation/IA | P1 |  | Onboarding outside main shell | Prototype available | Open Welcome/Goal/Placement. | Main bottom navigation is absent until main shell. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D007 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-NAV-003 | QA | Navigation/IA | P1 |  | Home purpose | Prototype available | Open Home. | Primary next action, reason and approximate duration are understandable. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-NAV-004 | QA | Navigation/IA | P1 |  | Learn purpose | Prototype available | Open Learn. | Finite cycle start/resume is prominent; no endless-feed affordance. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-NAV-005 | QA | Navigation/IA | P1 |  | Course purpose | Prototype available | Open Course. | Open/current/due/locked/preview states are distinguishable. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-NAV-006 | QA | Navigation/IA | P1 |  | Profile purpose | Prototype available | Open Profile. | Goal, qualitative evidence and settings are separated from mastery claims. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-NAV-007 | QA | Navigation/IA | P1 |  | Staff IA | Prototype available | Switch to staff surface. | Sidebar has Dashboard, Learners, Content, Interventions, Analytics, Administration. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-NAV-008 | QA | Navigation/IA | P1 |  | Publishing nested in Content | Prototype available | Open Content. | Publishing states are within Content lifecycle, not separate top-level product domain. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-NAV-009 | QA | Navigation/IA | P1 |  | Role visibility disclaimer | Prototype available | Inspect staff spec. | Docs state menu visibility is not authorization. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-NAV-010 | QA | Navigation/IA | P1 |  | Deep-link constraints | Prototype available | Inspect routing spec. | Deep-link rules require eligibility/permission re-check and no duplicate submit. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-001 | QA | Learner | P0 | PRD-01 | Start finite cycle | Home shows a recommendation | Select Start cycle and continue through roles. | Cycle has explicit intro, roles and summary; user explicitly chooses whether to continue. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-002 | QA | Learner | P1 | PRD-01 | Cycle progress visibility | Inside cycle | Observe progress indicator across steps. | Finite progress is visible and never suggests infinite scroll. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-003 | QA | Learner | P1 | PRD-13 | Objective and reason | Home/cycle intro | Inspect recommendation/cycle intro copy. | Objective and factual reason are visible; no inferred mental state. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-004 | QA | Learner | P1 | PRD-06 | Learn content is not mastery | Open Learn content step | Read explanation and continue. | UI does not mark objective mastered just for viewing explanation. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-005 | QA | Learner | P1 | PRD-02 | Retrieve answer selection | Open Retrieve | Select an option without submit. | Selection is visually distinct from submission/canonical result. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-006 | QA | Learner | P0 | PRD-02 | Wrong first response + retry | Practice retrieve item | Submit wrong answer, then retry correctly. | First wrong is acknowledged; retry is clearly practice and does not rewrite first response. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D001 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-007 | QA | Learner | P1 | PRD-02 | Retry exhausted state | Practice item after retry | Use retry then submit again. | No infinite retry loop; final feedback state is clear. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D005 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-008 | QA | Learner | P0 | PRD-03 | Hint assisted state | Practice item | Open/use hint then answer. | UI indicates assistance; copy does not present response as unaided. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D003 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-009 | QA | Learner | P0 | PRD-04 | Skip semantics | Practice item | Choose Skip for now and confirm. | No completion/mastery/reward is granted in copy; learner can continue safely. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-010 | QA | Learner | P1 | PRD-06 | Correct feedback tone | Practice item | Submit correct answer. | Feedback is concise/supportive without mastery overclaim. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-011 | QA | Learner | P1 | PRD-06 | Transfer step distinction | Reach Transfer | Compare Retrieve and Transfer wording/context. | Transfer changes cue/context and is not labelled as level-up. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-012 | QA | Learner | P1 | PRD-01 | Cycle summary | Complete cycle | Inspect summary. | Shows practiced evidence/needs review/next step, no fake mastery percentage. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-013 | QA | Learner | P0 | PRD-03 | Check has no pre-submit hint | Enter Check | Inspect available actions before submit. | Hint action is absent and Check context is explicit. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-014 | QA | Learner | P1 | PRD-05 | Listening Check policy copy | Open listening Check example/spec | Inspect play control and condition copy. | Offered play policy can be shown; UI never claims physical listening verification. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D008 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-015 | QA | Learner | P0 | PRD-09 | Placement optional | First-use onboarding | Choose skip placement. | Learner can continue with provisional/missing evidence state. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D007 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-016 | QA | Learner | P1 | PRD-09 | Placement result uncertainty | Complete/inspect placement result | Read result language. | Result is provisional and does not claim external CEFR certification. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D007 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-017 | QA | Learner | P1 | PRD-10 | Goal editing | Open Profile > Goal | Change goal. | Goal setting is presented as intent, not competence. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D017 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-018 | QA | Learner | P1 | PRD-13 | Locked objective preview | Open Course > locked objective | Open preview. | Preview is clearly non-progressing and shows prerequisite reason. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D013 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-019 | QA | Learner | P0 | PRD-16 | No recommendation fallback | Simulate recommendation unavailable | Open Home/Learn fallback. | A usable curriculum/due/manual action remains; no AI error dead end. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D018 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-020 | QA | Learner | P1 | PRD-16 | Nothing due state | Simulate no eligible item | Open empty state. | Honest empty/content-gap copy; no fabricated completion. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D018 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-STF-001 | QA | Staff | P1 |  | Staff dashboard shell | Staff surface available | Open Dashboard. | Operational overview is structured without pretending future data exists. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-STF-002 | QA | Staff | P1 |  | Learner list and detail | Staff surface | Open Learners then a learner. | List/detail IA works and evidence/activity sections are distinct. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-STF-003 | QA | Staff | P1 |  | No diagnosis language | Learner detail | Inspect copy. | No mental-state diagnosis or unsupported risk truth is presented. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-STF-004 | QA | Staff | P1 |  | Content lifecycle navigation | Content area | Open Library > Draft > Preview > Review > Published examples. | Lifecycle is understandable and revision states are explicit. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-STF-005 | QA | Staff | P1 |  | Draft vs published editability | Content area | Compare draft editor and published revision. | Draft is editable; published view offers create-new-draft rather than edit-in-place. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D009 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-STF-006 | QA | Staff | P1 | PRD-14 | Source/license gate | Draft editor | Open Source & License. | Missing provenance is visibly blocking for publish. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-STF-007 | QA | Staff | P1 | PRD-14 | Publish confirmation | Approved content | Open publish confirmation. | Copy explains immutable new revision; destructive ambiguity is avoided. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D009; P2-D014 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-STF-008 | QA | Staff | P1 |  | Intervention future boundary | Open Interventions | Inspect placeholder/state. | Does not imply Phase 11/12 implementation or causal outcome exists. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-STF-009 | QA | Staff | P1 |  | Analytics future boundary | Open Analytics | Inspect metric shell. | Requires time/source definition and does not display invented production metrics. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-STF-010 | QA | Staff | P1 |  | Administration authorization note | Open Administration | Inspect role/audit surfaces. | Design never claims sidebar visibility is sufficient authorization. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-OFF-001 | QA | Offline/System | P1 | PRD-15 | Offline banner | Learner home | Enable prototype offline toggle. | Offline state is visible but non-alarming; available offline actions remain usable. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-OFF-002 | QA | Offline/System | P0 | PRD-15 | Queued vs synced | Offline/online transitions | Submit/simulate queued action then restore connection. | Copy distinguishes saved on device / waiting to sync / synced. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D004 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-OFF-003 | QA | Offline/System | P0 | PRD-15 | Sync retry failure | Sync failure state | Open Sync Error and Retry. | Retry is safe and does not encourage duplicate manual submission. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D006 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-OFF-004 | QA | Offline/System | P0 | PRD-15 | Canonical refresh | Conflict/canonical refresh state | Inspect recovery action. | UI refetches canonical state rather than locally overriding server truth. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D006 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-OFF-005 | QA | Offline/System | P1 | PRD-15 | Media unavailable offline | Learning content | Simulate unavailable audio/media. | Valid alternative/sync action shown; no fabricated Check completion. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D006; P2-D019 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-OFF-006 | QA | Offline/System | P1 | PRD-15 | Re-auth state | Expired session placeholder | Open re-auth state. | User is told sign-in is required; local permission bypass is absent. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D006 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-BIZ-001 | QA | Business Integrity | P0 |  | Server authority language | All learner result surfaces | Inspect copy/states around submitting/sync. | UI does not imply local selection equals canonical scored result. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D004 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-BIZ-002 | QA | Business Integrity | P0 |  | Completion != mastery | Cycle summary/profile | Inspect completion/evidence language. | Completing a cycle is not labelled mastery/pass unless separate evidence supports it. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-BIZ-003 | QA | Business Integrity | P0 | PRD-04 | Skip != completion | Skip path | Complete a skip interaction. | No streak/mastery/completion reward copy appears. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-BIZ-004 | QA | Business Integrity | P0 | PRD-03 | Assisted != unaided | Hint path | Use hint then correct. | Assistance remains visible in evidence/feedback semantics. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D003 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-BIZ-005 | QA | Business Integrity | P0 | PRD-05 | Playback telemetry authority | Listening surfaces | Inspect replay language. | No statement says client replay count proves clean assessment. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-BIZ-006 | QA | Business Integrity | P0 | PRD-07 | Challenge bounded | Course/recommendation spec | Inspect challenge state/rule. | Challenge does not automatically change level/mastery/unlock. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-BIZ-007 | QA | Business Integrity | P0 | PRD-08 | Focus/prerequisite | Course/recommendation spec | Select locked/focus objective. | Prerequisite reason is clear and cannot be bypassed by preference. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-BIZ-008 | QA | Business Integrity | P0 | PRD-10 | Qualitative evidence | Profile/evidence | Inspect all evidence cards. | No fake mastery percentage or diagnosis. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-BIZ-009 | QA | Business Integrity | P0 | PRD-11 | Streak separate from learning evidence | Home/profile | Inspect streak/target presentation. | Streak is engagement and not shown as skill/mastery. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-BIZ-010 | QA | Business Integrity | P0 | PRD-12 | Rewards non-authoritative | Summary/reward surfaces | Inspect reward copy. | Rewards do not alter mastery/prerequisite/Check semantics. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-BIZ-011 | QA | Business Integrity | P0 | PRD-13 | Recommendation reason truthful | Home recommendation | Inspect reason copy for due/prerequisite/current. | Displayed reason matches defined reason category; no invented psychological cause. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-BIZ-012 | QA | Business Integrity | P0 | PRD-14 | Immutable revision UX | Staff Content | Inspect published revision actions. | No direct edit-in-place; new draft/revision workflow. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-BIZ-013 | QA | Business Integrity | P0 | PRD-15 | Lifecycle separation | Staff intervention/analytics spec | Inspect documented data lifecycle. | Decision/exposure/execution/outcome are not conflated. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-BIZ-014 | QA | Business Integrity | P0 | PRD-16 | ML-disabled fallback | Home/Learn | Simulate no recommendation. | Usable deterministic/manual learning flow remains. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D018 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-ACC-001 | QA | Accessibility/Responsive | P0 |  | Keyboard navigation staff | Desktop staff prototype | Navigate using Tab/Shift+Tab/Enter. | All primary navigation/actions reachable with visible focus. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D014 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-ACC-002 | QA | Accessibility/Responsive | P1 |  | Focus order learner | Learner prototype with keyboard | Tab through current screen. | Focus order follows visual/semantic order. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D014 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-ACC-003 | QA | Accessibility/Responsive | P0 |  | Touch targets | Learner screens | Inspect primary interactive targets. | Primary tap targets meet 48dp target; no critical tiny icon-only action. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-ACC-004 | QA | Accessibility/Responsive | P0 |  | Contrast | Design tokens/components | Check text/button/status combinations. | Target WCAG 2.2 AA contrast; semantic color never sole signal. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D015 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-ACC-005 | QA | Accessibility/Responsive | P1 |  | Text scaling | Learner layout | Simulate 200% browser text zoom as proxy. | Critical copy/actions remain readable without overlap/loss. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D020 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-ACC-006 | QA | Accessibility/Responsive | P1 |  | Reduced motion | Design system | Inspect motion spec. | Non-essential motion can be disabled/reduced. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-ACC-007 | QA | Accessibility/Responsive | P0 |  | Screen-reader names | Prototype controls | Inspect buttons/inputs. | Controls have meaningful labels/aria where needed. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D010 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-ACC-008 | QA | Accessibility/Responsive | P0 |  | Error identification | Forms/system states | Inspect errors. | Error is communicated by text/icon, not red color alone. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-ACC-009 | QA | Accessibility/Responsive | P1 |  | Learner small width | Set viewport ~360px | Open Home/Learn/Profile. | No horizontal overflow; primary actions visible. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D020 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-ACC-010 | QA | Accessibility/Responsive | P1 |  | Learner large phone | Set viewport ~480px | Open core screens. | Layout remains bounded/readable; no excessive line length. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-ACC-011 | QA | Accessibility/Responsive | P1 |  | Staff desktop | Set viewport 1440px | Open Staff Dashboard/Content. | Sidebar/content widths usable; tables readable. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-ACC-012 | QA | Accessibility/Responsive | P1 |  | Staff compact laptop | Set viewport 1024px | Open Staff Content. | Sidebar can compact; core task remains usable. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-HO-001 | QA | Handoff | P0 |  | Developer handoff completeness | Phase 2 package | Check routes, screen IDs, tokens, states, traceability and deferred boundaries. | Developer can implement Phase 3–5 UI without inventing missing interaction semantics. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D011 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-HO-002 | QA | Handoff | P1 |  | Token source | Design system | Compare spec and design_tokens.json. | Named tokens match; implementation can consume stable semantic names. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D015 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-HO-003 | QA | Handoff | P1 |  | Test ID guidance | Developer handoff | Inspect automation naming. | Recommended data-testid keys are stable and derived from screen/component IDs. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-HO-004 | QA | Handoff | P0 |  | No production code claim | Prototype/docs | Inspect release notes. | Prototype clearly labelled non-production and contains no backend business implementation. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-HO-005 | QA | Handoff | P0 |  | QA package signoff fields | QA workbook | Open Signoff sheet. | QC, QA, Product/Owner and Tech Lead fields exist with exit criteria. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence |  | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-021 | QA | Learner | P0 | PRD-01; PRD-04 | Required-response steps reject blank submit | Review/Transfer/Check item displayed with no option selected | Press Submit / Submit and continue / Submit Check without selecting an answer. | User remains on the item with accessible validation or an explicit Skip path; no answer/completion/evidence is fabricated. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D002 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-022 | QA | Learner | P1 | PRD-06 | Representative Grammar flow is executable | Grammar MVP objective available | Open Grammar Learn → Practice/Retrieve → Transfer → Check example. | Scaffold, guided practice, changed-context transfer and independent Check are concretely testable without inventing interaction semantics. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D016 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-LRN-023 | QA | Learner | P1 | PRD-05; PRD-06 | Representative Listening flow is executable | Listening MVP objective available | Open Listening Practice and Check; inspect playback, replay policy, offline-media and completion behavior. | Audio controls, offered-play policy, telemetry wording and media-unavailable behavior are concrete and testable; no physical-listening claim is made. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D008; P2-D019 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-STF-011 | QA | Staff | P1 | PRD-14 | Content publish lifecycle is executable end to end | Draft content with provenance issue exists | Edit draft → preview → submit review → resolve provenance → approve → confirm publish → inspect published revision → create new draft. | Every transition is executable; published revision is immutable and editing requires a new draft/revision. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D009 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-ACC-013 | QA | Accessibility/Responsive | P1 |  | Critical form fields have programmatic accessible names | Staff Content editor open | Inspect accessibility tree or equivalent name computation for Prompt and Source/license fields. | Each form control has a stable accessible name associated programmatically, not only visually adjacent text. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D010 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-HO-006 | QA | Handoff | P1 |  | Gate-critical Screen/State → QA mapping is explicit | Screen inventory, state catalog and QA suite available | Trace every gate-critical screen and state to at least one QA case; flag supporting-only screens explicitly. | Coverage can be audited without manually inferring screen IDs from prose. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D012 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.
QA-OFF-007 | QA | Offline/System | P0 | PRD-15 | Restored connectivity does not equal server-confirmed sync | A durable command is locally queued while offline | Restore network but withhold/mock server acknowledgement; then inspect summary and sync status. | State remains queued/syncing/retryable as appropriate; Synced appears only after authoritative acknowledgement/canonical refresh. | Independent QC/QA | PASS | Companion independent retest report + candidate evidence | P2-D004 | Independent PASS 2026-09-29. Exact candidate assets reproduced; local URL transport was policy-blocked, so browser cases loaded HTML/CSS/JS in-memory.

## 05_QC_Checklist
QC ARTIFACT CHECKLIST
Static conformity review before behavior QA.
QC ID | Check | Expected | Reviewer | Status | Evidence | Notes
QC-001 | Required Phase 2 artifacts exist | Every file in handoff index exists and opens. | Codex | PASS | evidence/codex/review/QC-001.json | Execution review; independent QC pending.
QC-002 | V3.2 remains untouched | No Phase 2 artifact silently modifies original V3.2 source. | Codex | PASS | evidence/codex/review/QC-002.json | Execution review; independent QC pending.
QC-003 | Phase boundary is explicit | Docs identify Phase 3+ behavior as future/deferred, not implemented. | Codex | PASS | evidence/codex/review/QC-003.json | Execution review; independent QC pending.
QC-004 | Screen IDs unique | All learner/staff screen IDs are unique and traceable. | Codex | PASS | evidence/codex/review/QC-004.json | Execution review; independent QC pending.
QC-005 | Routes documented | Every inventory screen has a route or overlay identity. | Codex | PASS | evidence/codex/review/QC-005.json | Execution review; independent QC pending.
QC-006 | PRD traceability complete | PRD-01..PRD-16 all map to UX surfaces and QA cases. | Codex | PASS | evidence/codex/review/QC-006.json | Execution review; independent QC pending.
QC-007 | Locked vs hypothesis language | 5m/retry/replay/placement thresholds are labelled hypotheses where applicable. | Codex | PASS | evidence/codex/review/QC-007.json | Execution review; independent QC pending.
QC-008 | No false learning claims | No precise mastery/diagnosis/efficacy claim appears in learner copy. | Codex | PASS | evidence/codex/review/QC-008.json | Execution review; independent QC pending.
QC-009 | No credential material | No password/token/secret URL in Phase 2 package. | Codex | PASS | evidence/codex/review/QC-009.json | Execution review; independent QC pending.
QC-010 | Prototype is self-contained | No external CDN/network dependency is required to render prototype. | Codex | PASS | evidence/codex/review/QC-010.json | Execution review; independent QC pending.

## 06_Defect_Log
PHASE 2 DEFECT LOG
Use P2-D###. Frozen-rule conflicts escalate, not silently redesigned.
Defect ID | Opened | Test ID | Screen/Component | Severity | Status | Title | Expected | Actual | Owner | Fix candidate | Retest result | Reviewer | Resolution
P2-D001 | 2026-09-27 | QA-LRN-006 | L-024 / prototype Retrieve | P0 | CLOSED | Retrieve marks the wrong answer as correct | Correct reply to “How are you?” must receive correct feedback; wrong distractors must not pass. | submitRetrieve() checks selected==='go'; value 'go' belongs to “Go to school.” while correct reply uses value 'good'. | UX/Prototype | Correct the answer key; use data-driven answer keys and regression-test every prototype item. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D002 | 2026-09-27 | QA-LRN-001; QA-BIZ-002 | Review / Transfer / Check | P0 | CLOSED | Blank submissions can advance and complete the learning cycle | Required-response steps must validate a selection or explicitly record Skip; Check must not complete without a response. | Review, Transfer and Check submit buttons call nextCycle() directly; no selection validation is required. | UX/Prototype | Add response validation plus separate submit/result/continue states; prevent false completion. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D003 | 2026-09-27 | QA-LRN-008; QA-BIZ-004 | L-024 Retrieve | P0 | CLOSED | Hint-assisted evidence is lost after submit | Once a hint is used, the response must remain tagged/presented as assisted through feedback/evidence semantics. | useHint() sets feedback='hint', but submit overwrites it with good/bad; final copy no longer carries assistance context. | UX/Prototype | Persist assisted=true independently from feedback; render assisted feedback/evidence and test hint→answer. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D004 | 2026-09-27 | QA-OFF-002; QA-BIZ-001 | L-060 / Summary | P1 | CLOSED | Network restoration is presented as Synced without server acknowledgement | LOCAL_QUEUED, SYNCING and SYNCED must be distinct; SYNCED requires authoritative acknowledgement/canonical state. | Prototype derives “Synced/All caught up” directly from offline=false, with no receipt/ack/canonical transition. | UX/Prototype | Model explicit sync states; show Synced only after simulated server acknowledgement. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D005 | 2026-09-27 | QA-LRN-007 | L-024 Retrieve | P1 | CLOSED | Retry can loop indefinitely | Practice retry policy must be bounded/configurable and expose a clear exhausted/final-feedback state. | Try once more resets selection/feedback with no retry counter or exhaustion state. | UX/Prototype | Add attempt counter/state and exhausted branch; preserve first-response evidence. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D006 | 2026-09-27 | QA-OFF-003; QA-OFF-004 | L-061 / canonical refresh | P1 | CLOSED | Mandatory offline recovery states are specified but not executable | Sync failure retry and canonical-refresh recovery must be reviewable/testable in the candidate. | Prototype only exposes offline waiting vs all-caught-up; no interactive retry failure/canonical refresh state. | UX/Prototype | Add prototype routes/state switches for retryable failure, partial sync, re-auth, canonical refresh and media unavailable. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D007 | 2026-09-27 | QA-NAV-002; QA-LRN-015 | Onboarding / placement | P1 | CLOSED | Onboarding and optional placement are not executable in prototype | Welcome → optional Goal → optional Placement → provisional result → Home must be testable without main-shell nav leakage. | Specs define the journey, but clickable prototype starts at Home and has no onboarding/placement route. | UX/Prototype | Prototype first-use path including skip-placement and provisional/missing-evidence result. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D008 | 2026-09-27 | QA-LRN-014 | Listening surfaces / C-012 | P1 | CLOSED | Listening assessment UX is not concretely represented | Listening Practice/Check should show offered-play policy, replay state, offline media behavior and non-authoritative client telemetry semantics. | AudioControl/listening rules exist in text, but the core clickable prototype has no listening item/control/state. | UX/Content | Add at least one listening Practice + Check example and media-unavailable state. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D009 | 2026-09-27 | QA-STF-004; QA-STF-007 | S-030..S-034 Content lifecycle | P1 | CLOSED | Staff review/publish lifecycle is not end-to-end testable | Draft → review → fix provenance → approve → publish confirmation → immutable published revision should be executable. | Preview has no handler; review approval is blocked without an interactive resolution path; publish confirmation is absent. | UX/Prototype | Implement the full prototype lifecycle and immutable revision confirmation path. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D010 | 2026-09-27 | QA-ACC-007 | Staff Content editor form | P1 | CLOSED | Staff editor inputs lack programmatic label association | Critical form controls must expose meaningful accessible names. | Visible labels are separate <label> elements without for/id binding; inputs have no aria-label/aria-labelledby. | UX/Accessibility | Bind label for/id (or equivalent accessible-name mechanism); test with accessibility tree/screen reader. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D011 | 2026-09-27 | QA-HO-001 | Screen specifications / developer handoff | P1 | CLOSED | Screen specification depth is insufficient for implementation without invention | Complex screens should define component composition, field/action contracts, validation, state transitions, permissions/dependencies and test hooks. | Inventory/spec rows define purpose/actions/states/rules, but complex authoring/assessment screens leave implementation-level interaction semantics underspecified. | Product/UX | Add per-screen anatomy + interaction/state tables for complex learner assessment and staff content screens. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D012 | 2026-09-27 | QA-HO-001 | Traceability model | P1 | CLOSED | QA traceability does not directly map screens/states to test cases | Every gate-critical screen/state should have explicit test coverage references. | 57 screens exist, but no screen ID appears explicitly in QA_TEST_CASES.csv; PRD traceability references 34/57 screens. | QA/Product | Create Screen ID → State → Requirement → QA case matrix; mark supporting-only screens explicitly. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D013 | 2026-09-27 | QA-LRN-018 | L-014 Course locked preview | P1 | CLOSED | Locked-objective Preview control is non-functional | Preview action should open a non-progressing preview and preserve prerequisite lock semantics. | Preview button is rendered without onclick/action. | UX/Prototype | Implement preview route/modal and prove no progress/unlock side effect. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D014 | 2026-09-27 | QA-ACC-001; QA-ACC-002 | Prototype accessibility semantics | P2 | CLOSED | Accessibility focus/live-region strategy needs refinement | Route changes, dynamic feedback and dialogs should announce only relevant changes and preserve predictable focus. | Whole SPA <main> is aria-live='polite'; no explicit route-change focus, modal focus trap/restore or targeted live-region strategy is documented. | UX/Accessibility | Use targeted status/error live regions and specify focus transfer/restore patterns for route changes, sheets and dialogs. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D015 | 2026-09-27 | QA-ACC-004 | Design token / CSS focus | P2 | CLOSED | Prototype focus indicator bypasses semantic focus token | Prototype should consume the semantic focus token consistently. | CSS defines --focus:#7C3AED but :focus-visible hardcodes #C4B5FD. | UX/Design System | Use var(--focus) or document a dedicated validated focus-ring token. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D016 | 2026-09-27 | QA-HO-001 | Learning content examples | P1 | CLOSED | Grammar learning UX is not concretely demonstrated | Phase 2 should demonstrate the chosen interaction/state pattern for Vocabulary, Grammar and Listening MVP domains. | Core prototype demonstrates simple greeting multiple-choice interactions but no grammar scaffold/practice/transfer/check example. | UX/Content | Add representative grammar flow with validation, feedback, assisted practice and independent Check. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D017 | 2026-09-27 | QA-LRN-017 | Phase 2 prototype | P1 | CLOSED | Goal editing unavailable | Preserve canonical case expectation | Profile had no editable goal action. | Codex | Edit goal, persist selection, clear goal and return to Profile. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D018 | 2026-09-27 | QA-LRN-019; QA-LRN-020 | Phase 2 prototype | P0 | CLOSED | Fallback/empty states not executable | Preserve canonical case expectation | No demo route/control could reach recommendation-unavailable or nothing-eligible state. | Codex | Executable demo controls; eligible cycle fallback and honest empty copy. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D019 | 2026-09-27 | QA-OFF-005; QA-LRN-023 | Phase 2 prototype | P1 | CLOSED | Missing-media practice Skip has no continuation | Preserve canonical case expectation | Skip records local state but media-blocked renderer hides result/Continue. | Codex | Render recorded skip and explicit Continue; Check still cannot skip. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D020 | 2026-09-27 | QA-ACC-005; QA-ACC-009 | Phase 2 prototype | P1 | CLOSED | 200% text clips learner actions | Preserve canonical case expectation | Learn Start and 320px bottom navigation clipped inside phone despite no document overflow. | Codex | Single-column narrow domain cards, bounded grids, wrapping and non-sticky demo bar; check ancestor clipping. | INDEPENDENT RETEST PASS | Independent QC/QA | Closed 2026-09-29 after clean static/artifact rerun and independent Chromium reproduction. See companion independent retest report.
P2-D021 | 2026-09-29 | Supplemental 320px / 200% text | Prototype QA toolbar (.prototype-bar/.prototype-controls) | P2 | DEFER CANDIDATE | Non-production prototype toolbar can create 328px document width at 320px viewport under 200% text on Linux Chromium | QA/prototype chrome should remain portable at the documented 320px/200% test condition, without masking product-surface results. | Independent Linux Chromium run: document scrollWidth=328px, caused only by prototype toolbar chips. Learner #app/phone remain 320px with zero overflowing descendants. | QA/Prototype | Either constrain/wrap toolbar chips for 320px/200%, or explicitly exclude non-production QA chrome from learner reflow assertions. | INDEPENDENT OBSERVATION | Independent QC/QA | Recommended ACCEPT/DEFER for Phase 2 product gate because learner product surface passes; does not reopen P2-D020.

## 07_Test_Run
TEST RUN SUMMARY
One row per candidate/run; preserve environment and evidence.
Run ID | Candidate/Commit | Date | Environment | Tester | Planned | Passed | Failed | Blocked | Pass rate | Evidence | Decision
CX-R1-20260927 | codex-r1 | 2026-09-27 | Windows / Chrome 153.0.8010.53 / fresh contexts | Codex | 94 | 94 | 0 | 0 | 100% | evidence/codex/execution_summary.json | RETEST CANDIDATE; NOT GATE PASS

## 08_Signoff
PHASE 2 SIGNOFF
Only complete after exit criteria. Signed Phase 2 makes Phase 3 eligible.
Role | Name | Decision | Date
QC Lead |  | PENDING
QA Lead |  | PENDING
Tech Lead |  | PENDING
Product/Owner |  | PENDING
Exit criterion | Required | Observed | Status | Evidence | Notes
P0 cases | 100% PASS | 44/44 Independent PASS | PASS | Companion independent retest report | Independent canonical reproduction.
Open P0/P1 defects | 0 | 0 open P0/P1 after independent closure | PASS | 06_Defect_Log | D001-D020 independently closed; D021 is P2 defer candidate.
Overall pass rate | ≥95% | 94/94 Independent PASS | PASS | Companion independent retest report | 74 browser + 20 artifact-review.
PRD traceability | 16/16 | 16/16 mapped | PASS | SCREEN_STATE_QA_TRACEABILITY.csv | Accepted by independent QC; Tech Lead acceptance still separate.
Accessibility mandatory | PASS | Keyboard/AX/reflow PASS; interactive speech/TalkBack BLOCKED | BLOCKED | Companion independent retest report | AX tree is not a substitute for interactive speech session.
Developer handoff | ACCEPTED | QA completeness PASS; Tech Lead acceptance pending | PENDING | 13_DEVELOPER_HANDOFF.md | Requires designated Tech Lead decision.
Product UX/UAT | ACCEPTED | PENDING | PENDING |  | Requires Product/Owner UAT/signoff.

## 09_Lists
CONTROLLED VALUES / REFERENCE
Stable enumerations used by QA workbook.
List | 1 | 2 | 3 | 4 | 5 | 6 | 7
Test status | NOT RUN | IN PROGRESS | PASS | FAIL | BLOCKED | DEFERRED
Severity | P0 | P1 | P2 | P3
Defect status | OPEN | IN PROGRESS | READY FOR RETEST | CLOSED | WONT FIX ACCEPTED | DUPLICATE
Signoff | PENDING | SIGNED | REJECTED
Run decision | IN PROGRESS | REJECTED | READY FOR SIGNOFF | ACCEPTED

## 10_Independent_Audit
MINGO — PHASE 2 INDEPENDENT QC/QA AUDIT
Audit date | 2026-09-27 | Decision | NOT PASSED — REWORK REQUIRED | Architecture | V3.2 unchanged
Method | Package integrity + static verifier + workbook audit + source-code interaction audit + evidence screenshot review + research benchmark
Important limitation | Fresh browser runtime navigation was blocked by this execution environment; source/state defects are deterministic, while unexecuted interactive cases remain NOT RUN/BLOCKED.
CONTROL METRICS | Observed | Interpretation | INDEPENDENT QA EXTENSION | Observed | Why
Manifest integrity | PASS | All files in candidate manifest verified. | Added cases | 7 | Cases added to catch coverage gaps found during audit.
Static artifact verifier | PASS | 57 screens / 18 components / 16 PRDs / 87 QA cases; no verifier errors. | New P0 cases | 2 | Blank-submit integrity; connectivity ≠ authoritative sync.
Prepared QA cases | 87 | 42 P0 + 45 P1. | New P1 cases | 5 | Grammar, Listening, publishing lifecycle, accessibility names, traceability.
Original execution state | 0/87 executed | Candidate was not QA-passed when delivered. | Current live total | 94 | 87 original + 7 independent gap/regression cases.
Screen→QA explicit mapping | 0/57 | No screen ID occurs explicitly in QA_TEST_CASES.csv. | Independent status | 10 PASS / 10 FAIL / 7 BLOCKED / 67 NOT RUN | After adding the new cases; full runtime execution still required.
PRD traceability screen references | 34/57 (59.6%) | Supporting screens may be valid, but state-level coverage is not demonstrable. | Open P0/P1 defects | 14 | 3 P0 + 11 P1; gate cannot pass.
Independent defects logged | 16 | P0/P1 must be closed before gate; P2 requires explicit acceptance if deferred. | P2 observations | 2 | May defer only with explicit acceptance after mandatory issues close.
GATE ASSESSMENT | Status | Reason
Package/provenance | PASS | Strong organization, checksums, V3.2 provenance and phase boundaries.
Learning integrity | FAIL | Wrong answer key, blank progression, assisted-state loss.
Offline/server-authority UX | FAIL | Network restoration is conflated with authoritative sync; mandatory recovery states not executable.
MVP domain coverage | FAIL | Listening and grammar interaction examples are not implementation-testable.
Staff content lifecycle | FAIL | Publish lifecycle is not end-to-end executable.
Accessibility readiness | FAIL/PENDING | Good target-size/contrast intent, but accessible names and focus/live-region strategy need repair and real testing.
Developer handoff | FAIL | Complex screen interaction contracts and screen/state→QA mapping remain underspecified.
Phase 2 gate | NOT PASSED | Open P0/P1 defects + mandatory P0 cases not fully passed + signoffs pending.
RESEARCH BENCHMARK | Implication for Mingo | Source
Retrieval practice | Keep Retrieve/Check meaningful and independent; correctness/evidence semantics are product-critical, not cosmetic. | Roediger & Karpicke (2006), PMID 16507066
Spacing | Due-review is scientifically defensible, but exact spacing policy remains a product hypothesis to validate. | Cepeda et al. (2006), PMID 16719566
Transfer | Transfer step has pedagogical value when cue/context genuinely changes. | Butler (2010), PMID 20804289
Adult L2 vocabulary | Avoid exposure-only design; combine spacing, retrieval and semantic/user-generated responses. | Rice & Tokowicz review, SSLA 2020, DOI 10.1017/S0272263119000500
Short sessions | Microlearning supports bite-sized targeted activity, but evidence does not justify hard-freezing exactly 5 minutes. | Heliyon systematic review (2024), DOI 10.1016/j.heliyon.2024.e41413
Autonomy | Optional goal/placement and explicit rationale are directionally sound; preserve learner choice without weakening prerequisites. | Contemporary Educational Psychology meta-analysis (2023), DOI 10.1016/j.cedpsych.2023.102235
Mobile accessibility | 48dp target baseline is appropriate for Android-first learner UI. | Android Developers accessibility guidance
Web accessibility | Contrast, 200% text resize and non-color-only semantics should remain gate checks. | WCAG 2.2
Gamification | Avoid assuming leaderboards/competition are universally beneficial; context and individual preference matter. | Ameen (2026) systematic review, DOI 10.1186/s40561-026-00447-z
REQUIRED REWORK ORDER | Acceptance condition
1. Learning-integrity blockers | Fix P2-D001..D003 and add regression cases for answer key, blank submit, hint-assisted evidence.
2. Offline authority states | Fix P2-D004/D006; demonstrate queued→syncing→acknowledged synced and error/canonical refresh.
3. MVP content interaction coverage | Add executable Listening + Grammar examples and first-use/placement flow.
4. Staff publishing | Make draft→review→provenance fix→approve→publish confirmation→published/new-draft executable.
5. Accessibility | Repair accessible names/focus semantics and run keyboard, screen-reader/TalkBack, contrast, 200% scale and viewport checks.
6. Handoff/traceability | Add detailed complex-screen contracts and Screen→State→QA mapping; then rerun all P0 and full suite.

## 11_Rework_R1
PHASE 2 REWORK R1 — FIX / RETEST CONTROL
All 16 audit findings have R1 source/spec fixes. Nothing is CLOSED until Codex execution and independent QC/QA retest provide evidence.
Defect | Severity | Finding | R1 source status | Fix evidence | Regression case | Codex obligation | QA closure owner
P2-D001 | P0 | Wrong Retrieve answer key | FIXED IN R1 | prototype/app.js | QA-LRN-006 | Codex browser regression | Independent QA retest
P2-D002 | P0 | Blank required-response progression | FIXED IN R1 | prototype/app.js + interaction contracts | QA-LRN-021; QA-BIZ-002 | Codex P0 regression | Independent QA retest
P2-D003 | P0 | Hint-assisted context lost | FIXED IN R1 | prototype/app.js | QA-LRN-008; QA-BIZ-004 | Codex P0 regression | Independent QA retest
P2-D004 | P1 | Network restoration shown as Synced | FIXED IN R1 | prototype/app.js + offline spec | QA-OFF-007; QA-OFF-002 | Codex offline regression | Independent QA retest
P2-D005 | P1 | Retry loop unbounded | FIXED IN R1 | prototype/app.js | QA-LRN-007 | Codex browser regression | Independent QA retest
P2-D006 | P1 | Offline recovery states not executable | FIXED IN R1 | prototype/app.js | QA-OFF-003; QA-OFF-004 | Codex state coverage | Independent QA retest
P2-D007 | P1 | Onboarding/placement not executable | FIXED IN R1 | prototype/app.js | QA-NAV-002; QA-LRN-015 | Codex first-use run | Independent QA retest
P2-D008 | P1 | Listening representative flow absent | FIXED IN R1 | prototype/app.js | QA-LRN-023; QA-LRN-014 | Codex listening run | Independent QA retest
P2-D009 | P1 | Publishing lifecycle incomplete | FIXED IN R1 | prototype/app.js | QA-STF-011; QA-STF-004 | Codex staff lifecycle | Independent QA retest
P2-D010 | P1 | Critical inputs lack accessible names | FIXED IN R1 | prototype/app.js | QA-ACC-013 | Accessibility tree check | Independent QA retest
P2-D011 | P1 | Complex screens underspecified | FIXED IN R1 | 15_COMPLEX_SCREEN_INTERACTION_CONTRACTS.md | QA-HO-001 | Tech/Codex handoff review | Independent QC
P2-D012 | P1 | Screen/state→QA traceability missing | FIXED IN R1 | SCREEN_STATE_QA_TRACEABILITY.csv | QA-HO-006 | Codex/static verifier | Independent QC
P2-D013 | P1 | Locked Preview non-functional | FIXED IN R1 | prototype/app.js | QA-LRN-018 | Codex browser regression | Independent QA retest
P2-D014 | P2 | Focus/live-region strategy weak | FIXED IN R1 | index/app + accessibility addendum | QA-ACC-001; QA-ACC-002 | Keyboard/screen-reader review | Independent QA
P2-D015 | P2 | Focus ring bypasses token | FIXED IN R1 | prototype/styles.css | QA-ACC-004; QA-HO-002 | Static/render check | Independent QC/QA
P2-D016 | P1 | Grammar representative flow absent | FIXED IN R1 | prototype/app.js | QA-LRN-022 | Codex grammar run | Independent QA retest

## 12_Codex_Execution
CODEX EXECUTION RECORD — MUST BE COMPLETED BEFORE QA RETEST
Codex records actual commands, environment, result and evidence. PASS cannot be copied from source-level fix status.
ID | Area | Execution | Priority | Status | Environment | Command / Method | Evidence path | Defect/New issue | Notes
CX-01 | Static | Run verify_phase2_rework.py | P0 | PASS | Windows / Chrome 153.0.8010.53 | See evidence and reproducible scripts | evidence/codex/rework_r1_static_checks_final.log |  | Execution only; no independent signoff.
CX-02 | Syntax | node --check prototype/app.js | P0 | PASS | Windows / Chrome 153.0.8010.53 | See evidence and reproducible scripts | evidence/codex/environment.json |  | Execution only; no independent signoff.
CX-03 | Browser P0 | D001 correct answer/distractor regression | P0 | PASS | Windows / Chrome 153.0.8010.53 | See evidence and reproducible scripts | evidence/codex/browser/QA-LRN-006.json |  | Execution only; no independent signoff.
CX-04 | Browser P0 | D002 blank Review/Transfer/Check cannot progress | P0 | PASS | Windows / Chrome 153.0.8010.53 | See evidence and reproducible scripts | evidence/codex/browser/QA-LRN-021.json |  | Execution only; no independent signoff.
CX-05 | Browser P0 | D003 assisted remains assisted | P0 | PASS | Windows / Chrome 153.0.8010.53 | See evidence and reproducible scripts | evidence/codex/browser/QA-LRN-008.json |  | Execution only; no independent signoff.
CX-06 | Offline P0 | Queued→online remains queued until server ack | P0 | PASS | Windows / Chrome 153.0.8010.53 | See evidence and reproducible scripts | evidence/codex/browser/QA-OFF-007.json |  | Execution only; no independent signoff.
CX-07 | Learner | First-use + optional placement | P1 | PASS | Windows / Chrome 153.0.8010.53 | See evidence and reproducible scripts | evidence/codex/browser/QA-LRN-016.json |  | Execution only; no independent signoff.
CX-08 | Learner | Representative Grammar flow | P1 | PASS | Windows / Chrome 153.0.8010.53 | See evidence and reproducible scripts | evidence/codex/browser/QA-LRN-022.json |  | Execution only; no independent signoff.
CX-09 | Learner | Representative Listening + media unavailable + Check play cap | P1 | PASS | Windows / Chrome 153.0.8010.53 | See evidence and reproducible scripts | evidence/codex/browser/QA-LRN-023.json |  | Execution only; no independent signoff.
CX-10 | Staff | Full publication lifecycle | P1 | PASS | Windows / Chrome 153.0.8010.53 | See evidence and reproducible scripts | evidence/codex/browser/QA-STF-011.json |  | Execution only; no independent signoff.
CX-11 | Accessibility | Accessible names / keyboard / modal focus restore / targeted live region | P1 | PASS | Windows / Chrome 153.0.8010.53 | See evidence and reproducible scripts | evidence/codex/browser/QA-ACC-013.json |  | AX and keyboard PASS. Screen-reader speech session BLOCKED.
CX-12 | Responsive | 200% scaling + learner widths + staff 1024/1440 | P1 | PASS | Windows / Chrome 153.0.8010.53 | See evidence and reproducible scripts | evidence/codex/supplemental/run.json |  | Execution only; no independent signoff.
CX-13 | QA Suite | Execute 94-case suite or record exact environment blockers | P0 | PASS | Windows / Chrome 153.0.8010.53 | See evidence and reproducible scripts | evidence/codex/execution_summary.json |  | Execution only; no independent signoff.
CX-14 | Packaging | Generate QA retest ZIP + SHA256 + manifest + filled handoff | P0 | PENDING |  |  | External ZIP .sha256 / .manifest.json |  | Final package integrity recorded in external sidecar after ZIP creation; no self-certifying hash in XLSX.

## 11_Independent_Retest_R1
MINGO — PHASE 2 R1 INDEPENDENT QC/QA RETEST
Audit date | 2026-09-29 | Verdict | TECHNICAL RETEST PASS / GATE HOLD | Phase 2 gate | NOT PASSED
Candidate SHA-256 | a1221923834cfeb84fd245e93694df2b78b85daf8f23eb6908b04cabe802be10 | Git commit | a112f762ab08f6fa688cc4857b21d95d1055ab5c | Architecture | V3.2.0 unchanged
Environment note | Localhost and file:// browser navigation were blocked by environment policy. Exact candidate HTML/CSS/JS were loaded into fresh Chromium documents in-memory; candidate source and assertions were not edited.
INDEPENDENT RESULTS | Result | Evidence / interpretation
ZIP hash + manifest | PASS | Actual ZIP hash matches sidecars; package manifest verifier PASS.
Static rework verifier | PASS | 57 screens / 18 components / 94 cases / 166 traceability rows; all 16 rework checks true.
Artifact review | 20/20 PASS | QC/review verifier independently rerun from clean extraction.
Browser canonical | 74/74 PASS | Fresh Chromium contexts; exact candidate assets loaded in-memory due navigation policy.
Canonical total | 94/94 PASS | 100% canonical pass.
P0 | 44/44 PASS | 100% P0 pass.
P2-D001..D020 | CLOSED | Independent functional/artifact retest accepted.
P2-D021 | DEFER CANDIDATE | 320px/200% document overflow is isolated to non-production prototype toolbar; learner #app remains 320px with zero overflowing descendants.
Interactive screen-reader/TalkBack | BLOCKED | Mandatory gate criterion remains unresolved; AX tree/keyboard checks are not a substitute.
Tech Lead signoff | PENDING | Developer-handoff acceptance must be recorded by designated Tech Lead.
Product/Owner UAT | PENDING | Product acceptance must be recorded by Product/Owner.
Phase 3 | DEFERRED | Not eligible until Phase 2 gate is formally passed.
GATE DECISION | Status | Reason
Functional/UX defect retest | PASS | Original 20 findings no longer block the gate.
Accessibility semantics/reflow | PASS WITH AT BLOCKER | Keyboard, AX names, focus, targeted live region and learner reflow pass; interactive speech session still required.
Developer handoff QC | PASS | Completeness/traceability checks pass; Tech Lead acceptance remains pending.
Overall Phase 2 gate | NOT PASSED | Mandatory interactive AT + Tech Lead + Product/Owner signoffs remain outstanding.
NEXT ACTION | Owner | Exit condition
Run real TalkBack/screen-reader session | QA/Accessibility | Representative learner + staff critical flows pass with recorded speech/focus evidence.
Accept developer handoff | Tech Lead | Tech Lead records ACCEPTED.
Run UAT and sign | Product/Owner | Product/Owner records SIGNED/ACCEPTED.
Resolve P2-D021 disposition | QA/Product | Explicit ACCEPT/DEFER or patch prototype toolbar and rerun four 320px supplemental checks.
Finalize Phase 2 gate | Governance | Only after all mandatory criteria are satisfied; then Phase 3 becomes eligible.